## Trang tính1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 15/8 | 16/8 | 100% | Nguyễn Đức Long
Carousel | 15/8 | 16/8 | 100% | Nguyễn Đức Long
Courses | 16/8 | 17/8 | 100% | Nguyễn Đức Long
Studious | 19/8 | 19/8 | 100% | Nguyễn Đức Long
Get Started |  |  |  | Nguyễn Đức Long
Services |  |  |  | Nguyễn Đức Long
Numbers | 19/8 | 20/8 | 100% | Nguyễn Anthony | 2022-09-01 | 2022-09-03 | 100%
Feedback | 21/8 | 21/8 | 100% | Nguyễn Anthony | 2022-09-01 | 2022-09-03 | 100%
Instructors | 22/8 | 25/8 | 100% | Nguyễn Anthony | 2022-09-02 | 2022-09-03 | 100%
Contact | 26/8 | 27/8 | 100% | Nguyễn Anthony | 2022-09-02 | 2022-09-03 | 100%
Footer | 29/8 | 30/8 | 100% | Nguyễn Anthony | 2022-09-03 | 2022-09-03 | 100%
Back-to-top | 31/8 | 31/8 | 100% | Nguyễn Anthony | 2022-09-03 | 2022-09-03 | 100%
Deploy project | 2022-09-03 | 2022-09-04 | 100% | Nguyễn Anthony | 2022-09-04 | 2022-09-04 | 100%